## Sheet1
Earned Value Analysis Template
Name:
Goal:
If we believe the variances (i.e., problems) encountered so far WILL continue for the remainder of our project, then the funds needed to complete the rest of our project is estimated to be? (ETC)
If we believe the variances (i.e., problems) encountered so far WILL continue for the remainder of our project, then the total budget to complete this project is estimated to be? (EAC)
TOTAL PLANNED PROJECT BUDGET | PHASE 1 (P1) - Gather Requirement | PHASE 2 (P2) | PHASE 3 (P3) | PHASE 4 (P4) | TOTAL
Task 1 | 4000 | 8000 | 4000 | 8000
Task 2 | 4000 | 8000 | 4000 | 8000
Task 3 | 4000 | 8000 | 4000 | 8000
Task 4 | 4000 | 8000 | 4000 | 8000
Task 5 | 4000 | 8000 | 4000 | 8000
TOTAL PLANNED PROJECT BUDGET | 20000 | 40000 | 20000 | 40000 | 120000
TASK
PHASE1 - Gather Client Requirements | Planned Value (PV) | Actual Cost (AC) | Earned Value (EV)
T1 Identify Business Clients | 4000 | 4000 | 4000
T2 Identify Current Business Processes | 4000 | 6000 | 4000
T3 Identify Current Systems/Interfaces | 4000 | 7000 | 4000
T4 Conduct Interviews | 4000
T5 Consolidate Requirements | 4000
TOTAL PHASE 1 | 20000 | 17000 | 12000
CALCULATE
Budget At Completion (BAC) | (Summation of Planned Value for Project)
Planned Value (PV) | PV = PV1 + PV2 +PV3 + PV4 + PV5 | 20000
Cost Variance (CV) | CV = EV - AC
Schedule Variance (SV) | SV = EV - PV
Cost Performance Index (CPI) | CPI = EV / AC
Schedule Performance Index (SPI) | SPI = EV / PV
Estimate To Completion (ETC) - CPI Only | ETC=(BAC – Cumulative EV to date)/Cumulative CPI
Estimate At Completion (EAC) - CPI Only | EAC = BAC / CPI
EAC = Cumulative AC + (BAC-Cumulative EV)/Cumulative CPI